## Task Tracker
🏭 PET FACTORY MAROC — Scope of Work Project Tracker
# | System | Spec | Phase / Task | Sub-Task | Owner | Status | Start | End | Weeks | Notes
SYSTEM 1 · Boiler System (6000 Kg/H)
1 | Boiler System | 6000 Kg/H | Design & Engineering | Technical Specs Review | Engineering | Complete | 2026-04-21 | 2026-05-04 | 2 | Verify steam output vs production demand
1 | Boiler System | 6000 Kg/H | Design & Engineering | P&ID Drawing Approval | Engineering | Complete | 2026-04-28 | 2026-05-11 | 2 | FAMSUN to submit by May 31
1 | Boiler System | 6000 Kg/H | Procurement | Vendor Finalization | Procurement | In Progress | 2026-05-11 | 2026-07-11 | 9
1 | Boiler System | 6000 Kg/H | Procurement | Purchase Order Issued | Procurement | Not Started | 2026-07-11 | 2026-07-18 | 2
1 | Boiler System | 6000 Kg/H | Procurement | Manufacturing & QC | Supplier | Not Started | 2026-07-18 | 2026-08-18 | 5 | Factory inspection at week 7
1 | Boiler System | 6000 Kg/H | Delivery & Logistics | Shipping / Sea Freight | Logistics | Not Started | 2026-08-18 | 2026-09-18 | 5
1 | Boiler System | 6000 Kg/H | Delivery & Logistics | Customs Clearance | Logistics | Not Started | 2026-09-18 | 2026-10-18 | 5
1 | Boiler System | 6000 Kg/H | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-10-18 | 2026-10-28 | 2
1 | Boiler System | 6000 Kg/H | Installation | Civil & Foundation Prep | Civil Contractor | Not Started | 2026-06-18 | 2026-08-02 | 7
1 | Boiler System | 6000 Kg/H | Installation | Equipment Installation | Install Team | Not Started | 2026-10-28 | 2026-11-08 | 2
1 | Boiler System | 6000 Kg/H | Installation | Piping & Connections | Install Team | Not Started | 2026-07-14 | 2026-08-14 | 5
1 | Boiler System | 6000 Kg/H | Testing & Commissioning | Factory Acceptance Test | Engineering | Not Started | 2026-11-08 | 2026-11-18 | 2 | At supplier factory
1 | Boiler System | 6000 Kg/H | Testing & Commissioning | Site Acceptance Test | Engineering | Not Started | 2026-11-18 | 2026-11-24 | 1
1 | Boiler System | 6000 Kg/H | Testing & Commissioning | Performance Verification | Engineering | Not Started | 2026-11-18 | 2026-11-24 | 1 | Confirm 6000 Kg/H output
SYSTEM 2 · Air Compressor System (37 kW ×2)
2 | Air Compressor System | 37 kW ×2 | Design & Engineering | Compressed Air Demand Audit | Engineering | Complete | 2026-04-21 | 2026-05-04 | 2
2 | Air Compressor System | 37 kW ×2 | Design & Engineering | Piping Layout Approval | Engineering | Complete | 2026-04-28 | 2026-05-11 | 2
2 | Air Compressor System | 37 kW ×2 | Procurement | Vendor Finalization | Procurement | In Progress | 2026-05-11 | 2026-07-11 | 9
2 | Air Compressor System | 37 kW ×2 | Procurement | Purchase Order Issued | Procurement | Not Started | 2026-07-11 | 2026-07-18 | 2
2 | Air Compressor System | 37 kW ×2 | Procurement | Manufacturing & QC | Supplier | Not Started | 2026-07-18 | 2026-08-18 | 5
2 | Air Compressor System | 37 kW ×2 | Delivery & Logistics | Shipping | Logistics | Not Started | 2026-08-18 | 2026-09-18 | 5
2 | Air Compressor System | 37 kW ×2 | Delivery & Logistics | Customs Clearance | Logistics | Not Started | 2026-09-18 | 2026-10-18 | 5
2 | Air Compressor System | 37 kW ×2 | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-10-18 | 2026-10-28 | 2
2 | Air Compressor System | 37 kW ×2 | Installation | Compressor Room Preparation | Civil Contractor | Not Started | 2026-06-18 | 2026-08-02 | 7 | Ventilation & cooling req.
2 | Air Compressor System | 37 kW ×2 | Installation | Equipment Installation | Install Team | Not Started | 2026-10-28 | 2026-11-08 | 2
2 | Air Compressor System | 37 kW ×2 | Installation | Pipe Network Connection | Install Team | Not Started | 2026-07-14 | 2026-08-14 | 5
2 | Air Compressor System | 37 kW ×2 | Testing & Commissioning | Pressure & Leak Test | Engineering | Not Started | 2026-11-08 | 2026-11-18 | 2
2 | Air Compressor System | 37 kW ×2 | Testing & Commissioning | Performance Verification | Engineering | Not Started | 2026-11-18 | 2026-11-24 | 1 | Confirm 4.3 m³/H
SYSTEM 3 · Water System (10000 Kg/H)
3 | Water System | 10000 Kg/H | Design & Engineering | Water Balance Study | Engineering | Complete | 2026-04-28 | 2026-05-11 | 2
3 | Water System | 10000 Kg/H | Design & Engineering | Plumbing Drawing Approval | Engineering | Complete | 2026-05-11 | 2026-07-11 | 9
3 | Water System | 10000 Kg/H | Procurement | Pump & Tank Selection | Procurement | In Progress | 2026-07-11 | 2026-07-18 | 2
3 | Water System | 10000 Kg/H | Procurement | Purchase Order Issued | Procurement | Not Started | 2026-07-18 | 2026-08-18 | 5
3 | Water System | 10000 Kg/H | Procurement | Manufacturing / Supply | Supplier | Not Started | 2026-08-18 | 2026-09-18 | 5
3 | Water System | 10000 Kg/H | Delivery & Logistics | Shipping | Logistics | Not Started | 2026-09-18 | 2026-10-18 | 5
3 | Water System | 10000 Kg/H | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-10-18 | 2026-10-28 | 2
3 | Water System | 10000 Kg/H | Installation | Trenching & Civil Works | Civil Contractor | Not Started | 2026-06-18 | 2026-08-02 | 7
3 | Water System | 10000 Kg/H | Installation | Pump & Tank Installation | Install Team | Not Started | 2026-10-28 | 2026-11-08 | 2
3 | Water System | 10000 Kg/H | Installation | Pipe Network Installation | Install Team | Not Started | 2026-07-14 | 2026-08-14 | 5
3 | Water System | 10000 Kg/H | Testing & Commissioning | Hydraulic Pressure Test | Engineering | Not Started | 2026-11-08 | 2026-11-18 | 2
3 | Water System | 10000 Kg/H | Testing & Commissioning | Flow Rate Verification | Engineering | Not Started | 2026-11-18 | 2026-11-24 | 1 | Confirm 2760 Kg/H
SYSTEM 4 · Weighbridge (60T)
4 | Weighbridge | 60T | Design & Engineering | Foundation Design | Engineering | Complete | 2026-07-11 | 2026-07-18 | 2 | 60T load capacity
4 | Weighbridge | 60T | Procurement | Supplier Selection | Procurement | Complete | 2026-07-18 | 2026-08-18 | 5
4 | Weighbridge | 60T | Procurement | Purchase Order Issued | Procurement | In Progress | 2026-08-18 | 2026-09-18 | 5
4 | Weighbridge | 60T | Procurement | Manufacturing | Supplier | Not Started | 2026-09-18 | 2026-10-18 | 5
4 | Weighbridge | 60T | Delivery & Logistics | Transport to Site | Logistics | Not Started | 2026-10-18 | 2026-10-28 | 2 | Heavy lift required
4 | Weighbridge | 60T | Installation | Foundation Construction | Civil Contractor | Not Started | 2026-06-18 | 2026-08-02 | 7
4 | Weighbridge | 60T | Installation | Weighbridge Installation | Install Team | Not Started | 2026-10-28 | 2026-11-08 | 2
4 | Weighbridge | 60T | Installation | Electrical & Data Wiring | Electrician | Not Started | 2026-07-14 | 2026-08-14 | 5
4 | Weighbridge | 60T | Testing & Commissioning | Calibration & Certification | Third Party | Not Started | 2026-11-08 | 2026-11-18 | 2 | Legal metrology certification
4 | Weighbridge | 60T | Testing & Commissioning | Operational Test | Engineering | Not Started | 2026-11-18 | 2026-11-24 | 1
SYSTEM 5 · Big Storage Oil Tank (2 × 20,000 L)
5 | Big Storage Oil Tank | 2 × 20,000 L | Design & Engineering | Tank Specs Review (Annex D) | Engineering | In Progress | 2026-04-21 | 2026-04-27 | 1 | Refer to Annex D
5 | Big Storage Oil Tank | 2 × 20,000 L | Design & Engineering | Civil Foundation Design | Engineering | Not Started | 2026-04-28 | 2026-05-11 | 2
5 | Big Storage Oil Tank | 2 × 20,000 L | Procurement | Vendor Finalization | Procurement | Not Started | 2026-04-28 | 2026-05-11 | 2
5 | Big Storage Oil Tank | 2 × 20,000 L | Procurement | Purchase Order Issued | Procurement | Not Started | 2026-05-12 | 2026-05-18 | 1
5 | Big Storage Oil Tank | 2 × 20,000 L | Procurement | Tank Fabrication | Supplier | Not Started | 2026-05-19 | 2026-07-13 | 8 | 40,000L total capacity
5 | Big Storage Oil Tank | 2 × 20,000 L | Delivery & Logistics | Oversized Transport Permit | Logistics | Not Started | 2026-07-07 | 2026-07-13 | 1 | Oversized load permit req.
5 | Big Storage Oil Tank | 2 × 20,000 L | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-07-14 | 2026-07-20 | 1
5 | Big Storage Oil Tank | 2 × 20,000 L | Installation | Civil Bund & Foundation | Civil Contractor | Not Started | 2026-06-02 | 2026-07-06 | 5 | Secondary containment bund
5 | Big Storage Oil Tank | 2 × 20,000 L | Installation | Tank Erection & Anchoring | Install Team | Not Started | 2026-07-14 | 2026-07-27 | 2
5 | Big Storage Oil Tank | 2 × 20,000 L | Installation | Pipework & Valves | Install Team | Not Started | 2026-07-28 | 2026-08-10 | 2
5 | Big Storage Oil Tank | 2 × 20,000 L | Testing & Commissioning | Hydrostatic Test | Engineering | Not Started | 2026-08-11 | 2026-08-17 | 1 | Leak integrity test
5 | Big Storage Oil Tank | 2 × 20,000 L | Testing & Commissioning | Regulatory Inspection | Third Party | Not Started | 2026-08-18 | 2026-08-24 | 1 | Fire safety & env. compliance
SYSTEM 6 · Elevator (2×2T)
6 | Elevator | 2×2T | Design & Engineering | Structural Drawing Review | Engineering | Complete | 2026-04-21 | 2026-05-04 | 2 | FAMSUN review by May 31
6 | Elevator | 2×2T | Design & Engineering | Drawing Mod Feedback to PFF | Engineering | Complete | 2026-04-28 | 2026-05-11 | 2
6 | Elevator | 2×2T | Procurement | Vendor/Supplier Finalization | Procurement | In Progress | 2026-05-11 | 2026-07-11 | 9
6 | Elevator | 2×2T | Procurement | Purchase Order Issued | Procurement | Not Started | 2026-07-11 | 2026-07-18 | 2
6 | Elevator | 2×2T | Procurement | Manufacturing | Supplier | Not Started | 2026-07-18 | 2026-08-18 | 5
6 | Elevator | 2×2T | Delivery & Logistics | Shipping | Logistics | Not Started | 2026-08-18 | 2026-09-18 | 5
6 | Elevator | 2×2T | Delivery & Logistics | Customs Clearance | Logistics | Not Started | 2026-09-18 | 2026-10-18 | 5
6 | Elevator | 2×2T | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-10-18 | 2026-10-28 | 2
6 | Elevator | 2×2T | Installation | Shaft / Structural Prep | Civil Contractor | Not Started | 2026-06-18 | 2026-08-02 | 7
6 | Elevator | 2×2T | Installation | Elevator Installation | Specialist | Not Started | 2026-10-28 | 2026-11-08 | 2 | Certified elevator installer
6 | Elevator | 2×2T | Installation | Electrical Connections | Electrician | Not Started | 2026-07-14 | 2026-08-14 | 5
6 | Elevator | 2×2T | Testing & Commissioning | Load Test (People & Goods) | Engineering | Not Started | 2026-11-08 | 2026-11-18 | 2 | Both use cases to be tested
6 | Elevator | 2×2T | Testing & Commissioning | Safety Inspection & Cert. | Third Party | Not Started | 2026-11-18 | 2026-11-24 | 1 | Regulatory certification req.
6 | Elevator | 2×2T | Testing & Commissioning | Handover & Training | Engineering | Not Started | 2026-11-18 | 2026-11-24 | 1
SYSTEM 7 · Electrical Installation & Transformer (1600 KVA)
7 | Electrical Installation & Transformer | 1600 KVA | Design & Engineering | Technical Specs Review | Engineering | Complete | 2026-04-21 | 2026-05-04 | 2
7 | Electrical Installation & Transformer | 1600 KVA | Design & Engineering | P&ID Drawing Approval | Engineering | Complete | 2026-04-28 | 2026-05-11 | 2 | FAMSUN to submit by May 31
7 | Electrical Installation & Transformer | 1600 KVA | Procurement | Vendor Finalization | Procurement | Complete | 2026-05-11 | 2026-05-12 | 1
7 | Electrical Installation & Transformer | 1600 KVA | Procurement | Purchase Order Issued | Procurement | Complete | 2026-06-11 | 2026-06-14 | 1
7 | Electrical Installation & Transformer | 1600 KVA | Procurement | Manufacturing & QC | Supplier | Not Started | 2026-07-01 | 2026-09-18 | 12 | Factory inspection at week 7
7 | Electrical Installation & Transformer | 1600 KVA | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-09-18 | 2026-09-20 | 1
7 | Electrical Installation & Transformer | 1600 KVA | Installation | Civil & Foundation Prep | Civil Contractor | Not Started | 2026-06-18 | 2026-08-02 | 7
7 | Electrical Installation & Transformer | 1600 KVA | Installation | Equipment Installation | Install Team | Not Started | 2026-06-22 | 2026-09-22 | 14
7 | Electrical Installation & Transformer | 1600 KVA | Installation | Piping & Connections | Install Team | Not Started | 2026-07-14 | 2026-08-14 | 5
7 | Electrical Installation & Transformer | 1600 KVA | Testing & Commissioning | Factory Acceptance Test | Engineering | Not Started | 2026-11-08 | 2026-11-18 | 2 | At supplier factory
7 | Electrical Installation & Transformer | 1600 KVA | Testing & Commissioning | Site Acceptance Test | Engineering | Not Started | 2026-11-18 | 2026-11-24 | 1
7 | Electrical Installation & Transformer | 1600 KVA | Testing & Commissioning | Performance Verification | Engineering | Not Started | 2026-11-18 | 2026-11-24 | 1 | Confirm 6000 Kg/H output
SYSTEM 8 · Aménagement Extérieur (Béton)
8 | Aménagement Extérieur | Béton | Design & Engineering | Technical Specs Review | Engineering | Complete | 2026-04-21 | 2026-05-04 | 2
8 | Aménagement Extérieur | Béton | Design & Engineering | P&ID Drawing Approval | Engineering | Complete | 2026-06-28 | 2026-07-11 | 2 | FAMSUN to submit by May 31
8 | Aménagement Extérieur | Béton | Procurement | Vendor Finalization | Procurement | In Progress | 2026-07-11 | 2026-10-11 | 14
SYSTEM 9 · Solaire Électricité (30% × 1600 KVA)
9 | Solaire Électricité | 30% × 1600 KVA | Design & Engineering | Technical Specs Review | Engineering | Not Started | 2026-04-21 | 2026-05-04 | 2
9 | Solaire Électricité | 30% × 1600 KVA | Design & Engineering | P&ID Drawing Approval | Engineering | Not Started | 2026-04-28 | 2026-05-11 | 2 | FAMSUN to submit by May 31
9 | Solaire Électricité | 30% × 1600 KVA | Procurement | Vendor Finalization | Procurement | Not Started | 2026-05-11 | 2026-07-11 | 9
9 | Solaire Électricité | 30% × 1600 KVA | Procurement | Purchase Order Issued | Procurement | Not Started | 2026-07-11 | 2026-07-18 | 2
9 | Solaire Électricité | 30% × 1600 KVA | Procurement | Manufacturing & QC | Supplier | Not Started | 2026-07-18 | 2026-08-18 | 5 | Factory inspection at week 7
9 | Solaire Électricité | 30% × 1600 KVA | Delivery & Logistics | Shipping / Sea Freight | Logistics | Not Started | 2026-08-18 | 2026-09-18 | 5
9 | Solaire Électricité | 30% × 1600 KVA | Delivery & Logistics | Customs Clearance | Logistics | Not Started | 2026-09-18 | 2026-10-18 | 5
9 | Solaire Électricité | 30% × 1600 KVA | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-10-18 | 2026-10-28 | 2
9 | Solaire Électricité | 30% × 1600 KVA | Installation | Civil & Foundation Prep | Civil Contractor | Not Started | 2026-06-18 | 2026-08-02 | 7
9 | Solaire Électricité | 30% × 1600 KVA | Installation | Equipment Installation | Install Team | Not Started | 2026-10-28 | 2026-11-08 | 2
9 | Solaire Électricité | 30% × 1600 KVA | Installation | Piping & Connections | Install Team | Not Started | 2026-07-14 | 2026-08-14 | 5
9 | Solaire Électricité | 30% × 1600 KVA | Testing & Commissioning | Factory Acceptance Test | Engineering | Not Started | 2026-11-08 | 2026-11-18 | 2 | At supplier factory
9 | Solaire Électricité | 30% × 1600 KVA | Testing & Commissioning | Site Acceptance Test | Engineering | Not Started | 2026-11-18 | 2026-11-24 | 1
9 | Solaire Électricité | 30% × 1600 KVA | Testing & Commissioning | Performance Verification | Engineering | Not Started | 2026-11-18 | 2026-11-24 | 1 | Confirm 6000 Kg/H output
SYSTEM 10 · Installation GAZ (15 m³)
10 | Installation GAZ | 15 m³ | Design & Engineering | Technical Specs Review | Engineering | Complete | 2026-04-21 | 2026-05-04 | 2
10 | Installation GAZ | 15 m³ | Design & Engineering | P&ID Drawing Approval | Engineering | Complete | 2026-06-28 | 2026-07-11 | 2 | FAMSUN to submit by May 31
10 | Installation GAZ | 15 m³ | Procurement | Vendor Finalization | Procurement | In Progress | 2026-07-11 | 2026-07-21 | 2
10 | Installation GAZ | 15 m³ | Procurement | Purchase Order Issued | Procurement | Not Started | 2026-07-21 | 2026-08-01 | 2
10 | Installation GAZ | 15 m³ | Procurement | Manufacturing & QC | Supplier | Not Started | 2026-08-01 | 2026-09-01 | 5 | Factory inspection at week 7
10 | Installation GAZ | 15 m³ | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-09-08 | 2026-09-09 | 1
10 | Installation GAZ | 15 m³ | Installation | Civil & Foundation Prep | Civil Contractor | Not Started | 2026-08-02 | 2026-09-02 | 5
10 | Installation GAZ | 15 m³ | Installation | Equipment Installation | Install Team | Not Started | 2026-09-10 | 2026-10-08 | 5
10 | Installation GAZ | 15 m³ | Installation | Piping & Connections | Install Team | Not Started | 2026-09-10 | 2026-10-08 | 5
10 | Installation GAZ | 15 m³ | Testing & Commissioning | Factory Acceptance Test | Engineering | Not Started | 2026-10-08 | 2026-10-09 | 1 | At supplier factory
10 | Installation GAZ | 15 m³ | Testing & Commissioning | Site Acceptance Test | Engineering | Not Started | 2026-11-18 | 2026-11-24 | 1
10 | Installation GAZ | 15 m³ | Testing & Commissioning | Performance Verification | Engineering | Not Started | 2026-11-18 | 2026-11-24 | 1
SYSTEM 11 · Séparation et Froid Industriel (Dry)
11 | Séparation et Froid Industriel | Dry | Design & Engineering | Technical Specs Review | Engineering | Complete | 2026-04-21 | 2026-05-04 | 2
11 | Séparation et Froid Industriel | Dry | Design & Engineering | P&ID Drawing Approval | Engineering | In Progress | 2026-06-28 | 2026-07-11 | 2 | FAMSUN to submit by May 31
11 | Séparation et Froid Industriel | Dry | Procurement | Vendor Finalization | Procurement | In Progress | 2026-07-11 | 2026-08-11 | 5
SYSTEM 12 · Séparation Salle de Commande & MCC (Dry)
12 | Séparation Salle de Commande & MCC | Dry | Design & Engineering | Technical Specs Review | Engineering | Complete | 2026-04-21 | 2026-05-04 | 2
12 | Séparation Salle de Commande & MCC | Dry | Design & Engineering | P&ID Drawing Approval | Engineering | Complete | 2026-04-28 | 2026-10-11 | 24 | FAMSUN to submit by May 31
12 | Séparation Salle de Commande & MCC | Dry | Procurement | Vendor Finalization | Procurement | In Progress | 2026-10-11 | 2026-11-11 | 5
SYSTEM 13 · Recrutement
13 | Recrutement | — | Responsable technique | CV | cv | Complete | 2026-04-21 | 2026-05-04 | 2
13 | Recrutement | — | Responsable qualité | CV | cv | Complete | 2026-04-21 | 2026-05-04 | 2
13 | Recrutement | — | ENTRETIEN | Finalization | Procurement | In Progress | 2026-07-01 | 2026-07-11 | 2
SYSTEM 14 · Logiciel
14 | Logiciel | — | Design & Engineering | Technical Specs Review | Engineering | Complete | 2026-04-21 | 2026-05-04 | 2
14 | Logiciel | — | Design & Engineering | P&ID Approval | Engineering | In Progress | 2026-04-28 | 2026-05-11 | 2
14 | Logiciel | — | Procurement | Vendor Finalization | Procurement | In Progress | 2026-05-11 | 2026-07-11 | 9

## Dashboard
📊 PET FACTORY MAROC — Project Dashboard
Key Metrics
Total Tasks |  | Complete |  | In Progress |  | Not Started
128 |  | 24 |  | 14 |  | 90
Overall Completion (weighted: Complete=100%, In Progress=50%)
Project % |  | 24.22%
System Summary
# | System | Spec | Total | Not Started | In Progress | Complete | % Complete
1 | Boiler System | 6000 Kg/H | 14 | 11 | 1 | 2 | 17.86%
2 | Air Compressor System | 37 kW ×2 | 13 | 10 | 1 | 2 | 19.23%
3 | Water System | 10000 Kg/H | 12 | 9 | 1 | 2 | 20.83%
4 | Weighbridge | 60T | 10 | 7 | 1 | 2 | 25%
5 | Big Storage Oil Tank | 2 × 20,000 L | 12 | 11 | 1 | 0 | 4.167%
6 | Elevator | 2×2T | 14 | 11 | 1 | 2 | 17.86%
7 | Electrical Installation & Transformer | 1600 KVA | 12 | 8 | 0 | 4 | 33.33%
8 | Aménagement Extérieur | Béton | 3 | 0 | 1 | 2 | 83.33%
9 | Solaire Électricité | 30% × 1600 KVA | 14 | 14 | 0 | 0 | 0%
10 | Installation GAZ | 15 m³ | 12 | 9 | 1 | 2 | 20.83%
11 | Séparation et Froid Industriel | Dry | 3 | 0 | 2 | 1 | 66.67%
12 | Séparation Salle de Commande & MCC | Dry | 3 | 0 | 1 | 2 | 83.33%
13 | Recrutement |  | 3 | 0 | 1 | 2 | 83.33%
14 | Logiciel |  | 3 | 0 | 2 | 1 | 66.67%
| TOTAL |  | 128 | 90 | 14 | 24 | 24.22%
Key Project Milestones
Date |  | Milestone |  |  |  |  | Status
2026-05-31 |  | FAMSUN Drawing Review Deadline (Boiler + Elevator) |  |  |  |  | Complete
2026-07-11 |  | Boiler / Compressor / Elevator Vendor Finalization |  |  |  |  | In Progress
2026-08-18 |  | Boiler & Elevator Manufacturing Complete |  |  |  |  | Not Started
2026-09-18 |  | Major Equipment Shipping Complete |  |  |  |  | Not Started
2026-10-28 |  | Site Deliveries Complete |  |  |  |  | Not Started
2026-11-08 |  | Equipment Installation Complete |  |  |  |  | Not Started
2026-11-24 |  | All Systems Tested & Commissioned — Facility Ready |  |  |  |  | Not Started
As of: |  | 2026-06-23

## Gantt Chart
📅 PET FACTORY MAROC — Dynamic Project Gantt (bars update automatically from Task Tracker dates & status)
# | System | Sub-Task | Status | Start | End | 2026-04-21 | 2026-04-28 | 2026-05-05 | 2026-05-12 | 2026-05-19 | 2026-05-26 | 2026-06-02 | 2026-06-09 | 2026-06-16 | 2026-06-23 | 2026-06-30 | 2026-07-07 | 2026-07-14 | 2026-07-21 | 2026-07-28 | 2026-08-04 | 2026-08-11 | 2026-08-18 | 2026-08-25 | 2026-09-01 | 2026-09-08 | 2026-09-15 | 2026-09-22 | 2026-09-29 | 2026-10-06 | 2026-10-13 | 2026-10-20 | 2026-10-27 | 2026-11-03 | 2026-11-10 | 2026-11-17 | 2026-11-24
▶ SYSTEM 1 — Boiler System (6000 Kg/H)
1 | Boiler System | Technical Specs Review | Complete | 2026-04-21 | 2026-05-04
1 | Boiler System | P&ID Drawing Approval | Complete | 2026-04-28 | 2026-05-11
1 | Boiler System | Vendor Finalization | In Progress | 2026-05-11 | 2026-07-11
1 | Boiler System | Purchase Order Issued | Not Started | 2026-07-11 | 2026-07-18
1 | Boiler System | Manufacturing & QC | Not Started | 2026-07-18 | 2026-08-18
1 | Boiler System | Shipping / Sea Freight | Not Started | 2026-08-18 | 2026-09-18
1 | Boiler System | Customs Clearance | Not Started | 2026-09-18 | 2026-10-18
1 | Boiler System | Site Delivery | Not Started | 2026-10-18 | 2026-10-28
1 | Boiler System | Civil & Foundation Prep | Not Started | 2026-06-18 | 2026-08-02
1 | Boiler System | Equipment Installation | Not Started | 2026-10-28 | 2026-11-08
1 | Boiler System | Piping & Connections | Not Started | 2026-07-14 | 2026-08-14
1 | Boiler System | Factory Acceptance Test | Not Started | 2026-11-08 | 2026-11-18
1 | Boiler System | Site Acceptance Test | Not Started | 2026-11-18 | 2026-11-24
1 | Boiler System | Performance Verification | Not Started | 2026-11-18 | 2026-11-24
▶ SYSTEM 2 — Air Compressor System (37 kW ×2)
2 | Air Compressor System | Compressed Air Demand Audit | Complete | 2026-04-21 | 2026-05-04
2 | Air Compressor System | Piping Layout Approval | Complete | 2026-04-28 | 2026-05-11
2 | Air Compressor System | Vendor Finalization | In Progress | 2026-05-11 | 2026-07-11
2 | Air Compressor System | Purchase Order Issued | Not Started | 2026-07-11 | 2026-07-18
2 | Air Compressor System | Manufacturing & QC | Not Started | 2026-07-18 | 2026-08-18
2 | Air Compressor System | Shipping | Not Started | 2026-08-18 | 2026-09-18
2 | Air Compressor System | Customs Clearance | Not Started | 2026-09-18 | 2026-10-18
2 | Air Compressor System | Site Delivery | Not Started | 2026-10-18 | 2026-10-28
2 | Air Compressor System | Compressor Room Preparation | Not Started | 2026-06-18 | 2026-08-02
2 | Air Compressor System | Equipment Installation | Not Started | 2026-10-28 | 2026-11-08
2 | Air Compressor System | Pipe Network Connection | Not Started | 2026-07-14 | 2026-08-14
2 | Air Compressor System | Pressure & Leak Test | Not Started | 2026-11-08 | 2026-11-18
2 | Air Compressor System | Performance Verification | Not Started | 2026-11-18 | 2026-11-24
▶ SYSTEM 3 — Water System (10000 Kg/H)
3 | Water System | Water Balance Study | Complete | 2026-04-28 | 2026-05-11
3 | Water System | Plumbing Drawing Approval | Complete | 2026-05-11 | 2026-07-11
3 | Water System | Pump & Tank Selection | In Progress | 2026-07-11 | 2026-07-18
3 | Water System | Purchase Order Issued | Not Started | 2026-07-18 | 2026-08-18
3 | Water System | Manufacturing / Supply | Not Started | 2026-08-18 | 2026-09-18
3 | Water System | Shipping | Not Started | 2026-09-18 | 2026-10-18
3 | Water System | Site Delivery | Not Started | 2026-10-18 | 2026-10-28
3 | Water System | Trenching & Civil Works | Not Started | 2026-06-18 | 2026-08-02
3 | Water System | Pump & Tank Installation | Not Started | 2026-10-28 | 2026-11-08
3 | Water System | Pipe Network Installation | Not Started | 2026-07-14 | 2026-08-14
3 | Water System | Hydraulic Pressure Test | Not Started | 2026-11-08 | 2026-11-18
3 | Water System | Flow Rate Verification | Not Started | 2026-11-18 | 2026-11-24
▶ SYSTEM 4 — Weighbridge (60T)
4 | Weighbridge | Foundation Design | Complete | 2026-07-11 | 2026-07-18
4 | Weighbridge | Supplier Selection | Complete | 2026-07-18 | 2026-08-18
4 | Weighbridge | Purchase Order Issued | In Progress | 2026-08-18 | 2026-09-18
4 | Weighbridge | Manufacturing | Not Started | 2026-09-18 | 2026-10-18
4 | Weighbridge | Transport to Site | Not Started | 2026-10-18 | 2026-10-28
4 | Weighbridge | Foundation Construction | Not Started | 2026-06-18 | 2026-08-02
4 | Weighbridge | Weighbridge Installation | Not Started | 2026-10-28 | 2026-11-08
4 | Weighbridge | Electrical & Data Wiring | Not Started | 2026-07-14 | 2026-08-14
4 | Weighbridge | Calibration & Certification | Not Started | 2026-11-08 | 2026-11-18
4 | Weighbridge | Operational Test | Not Started | 2026-11-18 | 2026-11-24
▶ SYSTEM 5 — Big Storage Oil Tank (2 × 20,000 L)
5 | Big Storage Oil Tank | Tank Specs Review (Annex D) | In Progress | 2026-04-21 | 2026-04-27
5 | Big Storage Oil Tank | Civil Foundation Design | Not Started | 2026-04-28 | 2026-05-11
5 | Big Storage Oil Tank | Vendor Finalization | Not Started | 2026-04-28 | 2026-05-11
5 | Big Storage Oil Tank | Purchase Order Issued | Not Started | 2026-05-12 | 2026-05-18
5 | Big Storage Oil Tank | Tank Fabrication | Not Started | 2026-05-19 | 2026-07-13
5 | Big Storage Oil Tank | Oversized Transport Permit | Not Started | 2026-07-07 | 2026-07-13
5 | Big Storage Oil Tank | Site Delivery | Not Started | 2026-07-14 | 2026-07-20
5 | Big Storage Oil Tank | Civil Bund & Foundation | Not Started | 2026-06-02 | 2026-07-06
5 | Big Storage Oil Tank | Tank Erection & Anchoring | Not Started | 2026-07-14 | 2026-07-27
5 | Big Storage Oil Tank | Pipework & Valves | Not Started | 2026-07-28 | 2026-08-10
5 | Big Storage Oil Tank | Hydrostatic Test | Not Started | 2026-08-11 | 2026-08-17
5 | Big Storage Oil Tank | Regulatory Inspection | Not Started | 2026-08-18 | 2026-08-24
▶ SYSTEM 6 — Elevator (2×2T)
6 | Elevator | Structural Drawing Review | Complete | 2026-04-21 | 2026-05-04
6 | Elevator | Drawing Mod Feedback to PFF | Complete | 2026-04-28 | 2026-05-11
6 | Elevator | Vendor/Supplier Finalization | In Progress | 2026-05-11 | 2026-07-11
6 | Elevator | Purchase Order Issued | Not Started | 2026-07-11 | 2026-07-18
6 | Elevator | Manufacturing | Not Started | 2026-07-18 | 2026-08-18
6 | Elevator | Shipping | Not Started | 2026-08-18 | 2026-09-18
6 | Elevator | Customs Clearance | Not Started | 2026-09-18 | 2026-10-18
6 | Elevator | Site Delivery | Not Started | 2026-10-18 | 2026-10-28
6 | Elevator | Shaft / Structural Prep | Not Started | 2026-06-18 | 2026-08-02
6 | Elevator | Elevator Installation | Not Started | 2026-10-28 | 2026-11-08
6 | Elevator | Electrical Connections | Not Started | 2026-07-14 | 2026-08-14
6 | Elevator | Load Test (People & Goods) | Not Started | 2026-11-08 | 2026-11-18
6 | Elevator | Safety Inspection & Cert. | Not Started | 2026-11-18 | 2026-11-24
6 | Elevator | Handover & Training | Not Started | 2026-11-18 | 2026-11-24
▶ SYSTEM 7 — Electrical Installation & Transformer (1600 KVA)
7 | Electrical Installation & Transformer | Technical Specs Review | Complete | 2026-04-21 | 2026-05-04
7 | Electrical Installation & Transformer | P&ID Drawing Approval | Complete | 2026-04-28 | 2026-05-11
7 | Electrical Installation & Transformer | Vendor Finalization | Complete | 2026-05-11 | 2026-05-12
7 | Electrical Installation & Transformer | Purchase Order Issued | Complete | 2026-06-11 | 2026-06-14
7 | Electrical Installation & Transformer | Manufacturing & QC | Not Started | 2026-07-01 | 2026-09-18
7 | Electrical Installation & Transformer | Site Delivery | Not Started | 2026-09-18 | 2026-09-20
7 | Electrical Installation & Transformer | Civil & Foundation Prep | Not Started | 2026-06-18 | 2026-08-02
7 | Electrical Installation & Transformer | Equipment Installation | Not Started | 2026-06-22 | 2026-09-22
7 | Electrical Installation & Transformer | Piping & Connections | Not Started | 2026-07-14 | 2026-08-14
7 | Electrical Installation & Transformer | Factory Acceptance Test | Not Started | 2026-11-08 | 2026-11-18
7 | Electrical Installation & Transformer | Site Acceptance Test | Not Started | 2026-11-18 | 2026-11-24
7 | Electrical Installation & Transformer | Performance Verification | Not Started | 2026-11-18 | 2026-11-24
▶ SYSTEM 8 — Aménagement Extérieur (Béton)
8 | Aménagement Extérieur | Technical Specs Review | Complete | 2026-04-21 | 2026-05-04
8 | Aménagement Extérieur | P&ID Drawing Approval | Complete | 2026-06-28 | 2026-07-11
8 | Aménagement Extérieur | Vendor Finalization | In Progress | 2026-07-11 | 2026-10-11
▶ SYSTEM 9 — Solaire Électricité (30% × 1600 KVA)
9 | Solaire Électricité | Technical Specs Review | Not Started | 2026-04-21 | 2026-05-04
9 | Solaire Électricité | P&ID Drawing Approval | Not Started | 2026-04-28 | 2026-05-11
9 | Solaire Électricité | Vendor Finalization | Not Started | 2026-05-11 | 2026-07-11
9 | Solaire Électricité | Purchase Order Issued | Not Started | 2026-07-11 | 2026-07-18
9 | Solaire Électricité | Manufacturing & QC | Not Started | 2026-07-18 | 2026-08-18
9 | Solaire Électricité | Shipping / Sea Freight | Not Started | 2026-08-18 | 2026-09-18
9 | Solaire Électricité | Customs Clearance | Not Started | 2026-09-18 | 2026-10-18
9 | Solaire Électricité | Site Delivery | Not Started | 2026-10-18 | 2026-10-28
9 | Solaire Électricité | Civil & Foundation Prep | Not Started | 2026-06-18 | 2026-08-02
9 | Solaire Électricité | Equipment Installation | Not Started | 2026-10-28 | 2026-11-08
9 | Solaire Électricité | Piping & Connections | Not Started | 2026-07-14 | 2026-08-14
9 | Solaire Électricité | Factory Acceptance Test | Not Started | 2026-11-08 | 2026-11-18
9 | Solaire Électricité | Site Acceptance Test | Not Started | 2026-11-18 | 2026-11-24
9 | Solaire Électricité | Performance Verification | Not Started | 2026-11-18 | 2026-11-24
▶ SYSTEM 10 — Installation GAZ (15 m³)
10 | Installation GAZ | Technical Specs Review | Complete | 2026-04-21 | 2026-05-04
10 | Installation GAZ | P&ID Drawing Approval | Complete | 2026-06-28 | 2026-07-11
10 | Installation GAZ | Vendor Finalization | In Progress | 2026-07-11 | 2026-07-21
10 | Installation GAZ | Purchase Order Issued | Not Started | 2026-07-21 | 2026-08-01
10 | Installation GAZ | Manufacturing & QC | Not Started | 2026-08-01 | 2026-09-01
10 | Installation GAZ | Site Delivery | Not Started | 2026-09-08 | 2026-09-09
10 | Installation GAZ | Civil & Foundation Prep | Not Started | 2026-08-02 | 2026-09-02
10 | Installation GAZ | Equipment Installation | Not Started | 2026-09-10 | 2026-10-08
10 | Installation GAZ | Piping & Connections | Not Started | 2026-09-10 | 2026-10-08
10 | Installation GAZ | Factory Acceptance Test | Not Started | 2026-10-08 | 2026-10-09
10 | Installation GAZ | Site Acceptance Test | Not Started | 2026-11-18 | 2026-11-24
10 | Installation GAZ | Performance Verification | Not Started | 2026-11-18 | 2026-11-24
▶ SYSTEM 11 — Séparation et Froid Industriel (Dry)
11 | Séparation et Froid Industriel | Technical Specs Review | Complete | 2026-04-21 | 2026-05-04
11 | Séparation et Froid Industriel | P&ID Drawing Approval | In Progress | 2026-06-28 | 2026-07-11
11 | Séparation et Froid Industriel | Vendor Finalization | In Progress | 2026-07-11 | 2026-08-11
▶ SYSTEM 12 — Séparation Salle de Commande & MCC (Dry)
12 | Séparation Salle de Commande & MCC | Technical Specs Review | Complete | 2026-04-21 | 2026-05-04
12 | Séparation Salle de Commande & MCC | P&ID Drawing Approval | Complete | 2026-04-28 | 2026-10-11
12 | Séparation Salle de Commande & MCC | Vendor Finalization | In Progress | 2026-10-11 | 2026-11-11
▶ SYSTEM 13 — Recrutement
13 | Recrutement | CV | Complete | 2026-04-21 | 2026-05-04
13 | Recrutement | CV | Complete | 2026-04-21 | 2026-05-04
13 | Recrutement | Finalization | In Progress | 2026-07-01 | 2026-07-11
▶ SYSTEM 14 — Logiciel
14 | Logiciel | Technical Specs Review | Complete | 2026-04-21 | 2026-05-04
14 | Logiciel | P&ID Approval | In Progress | 2026-04-28 | 2026-05-11
14 | Logiciel | Vendor Finalization | In Progress | 2026-05-11 | 2026-07-11
LEGEND: |  | Complete |  |  | In Progress |  |  | Not Started |  |  | Blocked |  |  | Today (band)