## Task Tracker
🏭 PET FACTORY MAROC — Scope of Work Project Tracker
# | System | Spec | Phase / Task | Sub-Task | Owner | Status | Start | End | Weeks | Notes
SYSTEM 1 · Boiler System (2123 Kg/H)
1 | Boiler System | 2123 Kg/H | Design & Engineering | Technical Specs Review | Engineering | In Progress | 2026-04-21 | 2026-05-04 | 2 | Verify steam output vs production demand
1 | Boiler System | 2123 Kg/H | Design & Engineering | P&ID Drawing Approval | Engineering | Not Started | 2026-04-28 | 2026-05-11 | 2 | FAMSUN to submit by May 31
1 | Boiler System | 2123 Kg/H | Procurement | Vendor Finalization | Procurement | Complete | 2026-04-21 | 2026-04-27 | 1
1 | Boiler System | 2123 Kg/H | Procurement | Purchase Order Issued | Procurement | Complete | 2026-04-28 | 2026-05-04 | 1
1 | Boiler System | 2123 Kg/H | Procurement | Manufacturing & QC | Supplier | In Progress | 2026-05-05 | 2026-06-15 | 6 | Factory inspection at week 7
1 | Boiler System | 2123 Kg/H | Delivery & Logistics | Shipping / Sea Freight | Logistics | Not Started | 2026-06-16 | 2026-07-06 | 3
1 | Boiler System | 2123 Kg/H | Delivery & Logistics | Customs Clearance | Logistics | Not Started | 2026-07-07 | 2026-07-13 | 1
1 | Boiler System | 2123 Kg/H | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-07-14 | 2026-07-20 | 1
1 | Boiler System | 2123 Kg/H | Installation | Civil & Foundation Prep | Civil Contractor | Not Started | 2026-06-30 | 2026-07-20 | 3
1 | Boiler System | 2123 Kg/H | Installation | Equipment Installation | Install Team | Not Started | 2026-07-21 | 2026-08-03 | 2
1 | Boiler System | 2123 Kg/H | Installation | Piping & Connections | Install Team | Not Started | 2026-08-04 | 2026-08-17 | 2
1 | Boiler System | 2123 Kg/H | Testing & Commissioning | Factory Acceptance Test | Engineering | Not Started | 2026-06-02 | 2026-06-08 | 1 | At supplier factory
1 | Boiler System | 2123 Kg/H | Testing & Commissioning | Site Acceptance Test | Engineering | Not Started | 2026-08-18 | 2026-08-24 | 1
1 | Boiler System | 2123 Kg/H | Testing & Commissioning | Performance Verification | Engineering | Not Started | 2026-08-25 | 2026-08-31 | 1 | Confirm 2123 Kg/H output
SYSTEM 2 · Air Compressor System (4.3 m³/H)
2 | Air Compressor System | 4.3 m³/H | Design & Engineering | Compressed Air Demand Audit | Engineering | In Progress | 2026-04-21 | 2026-04-27 | 1
2 | Air Compressor System | 4.3 m³/H | Design & Engineering | Piping Layout Approval | Engineering | Not Started | 2026-04-28 | 2026-05-11 | 2
2 | Air Compressor System | 4.3 m³/H | Procurement | Vendor Finalization | Procurement | Complete | 2026-04-21 | 2026-04-27 | 1
2 | Air Compressor System | 4.3 m³/H | Procurement | Purchase Order Issued | Procurement | In Progress | 2026-04-28 | 2026-05-04 | 1
2 | Air Compressor System | 4.3 m³/H | Procurement | Manufacturing & QC | Supplier | Not Started | 2026-05-05 | 2026-06-01 | 4
2 | Air Compressor System | 4.3 m³/H | Delivery & Logistics | Shipping | Logistics | Not Started | 2026-06-02 | 2026-06-22 | 3
2 | Air Compressor System | 4.3 m³/H | Delivery & Logistics | Customs Clearance | Logistics | Not Started | 2026-06-23 | 2026-06-29 | 1
2 | Air Compressor System | 4.3 m³/H | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-06-30 | 2026-07-06 | 1
2 | Air Compressor System | 4.3 m³/H | Installation | Compressor Room Preparation | Civil Contractor | Not Started | 2026-06-16 | 2026-06-29 | 2 | Ventilation & cooling req.
2 | Air Compressor System | 4.3 m³/H | Installation | Equipment Installation | Install Team | Not Started | 2026-07-07 | 2026-07-13 | 1
2 | Air Compressor System | 4.3 m³/H | Installation | Pipe Network Connection | Install Team | Not Started | 2026-07-14 | 2026-07-27 | 2
2 | Air Compressor System | 4.3 m³/H | Testing & Commissioning | Pressure & Leak Test | Engineering | Not Started | 2026-07-28 | 2026-08-03 | 1
2 | Air Compressor System | 4.3 m³/H | Testing & Commissioning | Performance Verification | Engineering | Not Started | 2026-08-04 | 2026-08-10 | 1 | Confirm 4.3 m³/H
SYSTEM 3 · Water System (2760 Kg/H)
3 | Water System | 2760 Kg/H | Design & Engineering | Water Balance Study | Engineering | In Progress | 2026-04-21 | 2026-05-04 | 2
3 | Water System | 2760 Kg/H | Design & Engineering | Plumbing Drawing Approval | Engineering | Not Started | 2026-04-28 | 2026-05-11 | 2
3 | Water System | 2760 Kg/H | Procurement | Pump & Tank Selection | Procurement | Not Started | 2026-04-28 | 2026-05-11 | 2
3 | Water System | 2760 Kg/H | Procurement | Purchase Order Issued | Procurement | Not Started | 2026-05-12 | 2026-05-18 | 1
3 | Water System | 2760 Kg/H | Procurement | Manufacturing / Supply | Supplier | Not Started | 2026-05-19 | 2026-06-15 | 4
3 | Water System | 2760 Kg/H | Delivery & Logistics | Shipping | Logistics | Not Started | 2026-06-16 | 2026-06-29 | 2
3 | Water System | 2760 Kg/H | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-06-30 | 2026-07-06 | 1
3 | Water System | 2760 Kg/H | Installation | Trenching & Civil Works | Civil Contractor | Not Started | 2026-06-23 | 2026-07-13 | 3
3 | Water System | 2760 Kg/H | Installation | Pump & Tank Installation | Install Team | Not Started | 2026-07-07 | 2026-07-20 | 2
3 | Water System | 2760 Kg/H | Installation | Pipe Network Installation | Install Team | Not Started | 2026-07-21 | 2026-08-03 | 2
3 | Water System | 2760 Kg/H | Testing & Commissioning | Hydraulic Pressure Test | Engineering | Not Started | 2026-08-04 | 2026-08-10 | 1
3 | Water System | 2760 Kg/H | Testing & Commissioning | Flow Rate Verification | Engineering | Not Started | 2026-08-11 | 2026-08-17 | 1 | Confirm 2760 Kg/H
SYSTEM 4 · Weighbridge (60T)
4 | Weighbridge | 60T | Design & Engineering | Foundation Design | Engineering | Not Started | 2026-05-05 | 2026-05-18 | 2 | 60T load capacity
4 | Weighbridge | 60T | Procurement | Supplier Selection | Procurement | Not Started | 2026-04-28 | 2026-05-11 | 2
4 | Weighbridge | 60T | Procurement | Purchase Order Issued | Procurement | Not Started | 2026-05-12 | 2026-05-18 | 1
4 | Weighbridge | 60T | Procurement | Manufacturing | Supplier | Not Started | 2026-05-19 | 2026-06-29 | 6
4 | Weighbridge | 60T | Delivery & Logistics | Transport to Site | Logistics | Not Started | 2026-06-30 | 2026-07-06 | 1 | Heavy lift required
4 | Weighbridge | 60T | Installation | Foundation Construction | Civil Contractor | Not Started | 2026-05-19 | 2026-06-15 | 4
4 | Weighbridge | 60T | Installation | Weighbridge Installation | Install Team | Not Started | 2026-06-30 | 2026-07-13 | 2
4 | Weighbridge | 60T | Installation | Electrical & Data Wiring | Electrician | Not Started | 2026-07-14 | 2026-07-20 | 1
4 | Weighbridge | 60T | Testing & Commissioning | Calibration & Certification | Third Party | Not Started | 2026-07-21 | 2026-07-27 | 1 | Legal metrology certification
4 | Weighbridge | 60T | Testing & Commissioning | Operational Test | Engineering | Not Started | 2026-07-28 | 2026-08-03 | 1
SYSTEM 5 · Big Storage Oil Tank (2 × 20,000 L)
5 | Big Storage Oil Tank | 2 × 20,000 L | Design & Engineering | Tank Specs Review (Annex D) | Engineering | In Progress | 2026-04-21 | 2026-04-27 | 1 | Refer to Annex D
5 | Big Storage Oil Tank | 2 × 20,000 L | Design & Engineering | Civil Foundation Design | Engineering | Not Started | 2026-04-28 | 2026-05-11 | 2
5 | Big Storage Oil Tank | 2 × 20,000 L | Procurement | Vendor Finalization | Procurement | Not Started | 2026-04-28 | 2026-05-11 | 2
5 | Big Storage Oil Tank | 2 × 20,000 L | Procurement | Purchase Order Issued | Procurement | Not Started | 2026-05-12 | 2026-05-18 | 1
5 | Big Storage Oil Tank | 2 × 20,000 L | Procurement | Tank Fabrication | Supplier | Not Started | 2026-05-19 | 2026-07-13 | 8 | 40,000L total capacity
5 | Big Storage Oil Tank | 2 × 20,000 L | Delivery & Logistics | Oversized Transport Permit | Logistics | Not Started | 2026-07-07 | 2026-07-13 | 1 | Oversized load permit req.
5 | Big Storage Oil Tank | 2 × 20,000 L | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-07-14 | 2026-07-20 | 1
5 | Big Storage Oil Tank | 2 × 20,000 L | Installation | Civil Bund & Foundation | Civil Contractor | Not Started | 2026-06-02 | 2026-07-06 | 5 | Secondary containment bund
5 | Big Storage Oil Tank | 2 × 20,000 L | Installation | Tank Erection & Anchoring | Install Team | Not Started | 2026-07-14 | 2026-07-27 | 2
5 | Big Storage Oil Tank | 2 × 20,000 L | Installation | Pipework & Valves | Install Team | Not Started | 2026-07-28 | 2026-08-10 | 2
5 | Big Storage Oil Tank | 2 × 20,000 L | Testing & Commissioning | Hydrostatic Test | Engineering | Not Started | 2026-08-11 | 2026-08-17 | 1 | Leak integrity test
5 | Big Storage Oil Tank | 2 × 20,000 L | Testing & Commissioning | Regulatory Inspection | Third Party | Not Started | 2026-08-18 | 2026-08-24 | 1 | Fire safety & env. compliance
SYSTEM 6 · Elevator (2×2T)
6 | Elevator | 2×2T | Design & Engineering | Structural Drawing Review | Engineering | In Progress | 2026-04-21 | 2026-05-04 | 2 | FAMSUN review by May 31
6 | Elevator | 2×2T | Design & Engineering | Drawing Mod Feedback to PFF | Engineering | Not Started | 2026-05-05 | 2026-05-11 | 1
6 | Elevator | 2×2T | Procurement | Vendor/Supplier Finalization | Procurement | Not Started | 2026-04-28 | 2026-05-11 | 2
6 | Elevator | 2×2T | Procurement | Purchase Order Issued | Procurement | Not Started | 2026-05-12 | 2026-05-18 | 1
6 | Elevator | 2×2T | Procurement | Manufacturing | Supplier | Not Started | 2026-05-19 | 2026-07-13 | 8
6 | Elevator | 2×2T | Delivery & Logistics | Shipping | Logistics | Not Started | 2026-07-14 | 2026-08-03 | 3
6 | Elevator | 2×2T | Delivery & Logistics | Customs Clearance | Logistics | Not Started | 2026-08-04 | 2026-08-10 | 1
6 | Elevator | 2×2T | Delivery & Logistics | Site Delivery | Logistics | Not Started | 2026-08-11 | 2026-08-17 | 1
6 | Elevator | 2×2T | Installation | Shaft / Structural Prep | Civil Contractor | Not Started | 2026-06-16 | 2026-07-20 | 5
6 | Elevator | 2×2T | Installation | Elevator Installation | Specialist | Not Started | 2026-08-11 | 2026-08-31 | 3 | Certified elevator installer
6 | Elevator | 2×2T | Installation | Electrical Connections | Electrician | Not Started | 2026-08-25 | 2026-08-31 | 1
6 | Elevator | 2×2T | Testing & Commissioning | Load Test (People & Goods) | Engineering | Not Started | 2026-09-01 | 2026-09-07 | 1 | Both use cases to be tested
6 | Elevator | 2×2T | Testing & Commissioning | Safety Inspection & Cert. | Third Party | Not Started | 2026-09-08 | 2026-09-14 | 1 | Regulatory certification req.
6 | Elevator | 2×2T | Testing & Commissioning | Handover & Training | Engineering | Not Started | 2026-09-15 | 2026-09-21 | 1

## Gantt Chart
🏭 PET FACTORY MAROC — Project Gantt Chart ¦ Start: Apr 21, 2026
# | System | Phase | Sub-Task | Owner | Status | Wk1 Apr21 | Wk2 Apr28 | Wk3 May05 | Wk4 May12 | Wk5 May19 | Wk6 May26 | Wk7 Jun02 | Wk8 Jun09 | Wk9 Jun16 | Wk10 Jun23 | Wk11 Jun30 | Wk12 Jul07 | Wk13 Jul14 | Wk14 Jul21 | Wk15 Jul28 | Wk16 Aug04 | Wk17 Aug11 | Wk18 Aug18 | Wk19 Aug25 | Wk20 Sep01 | Wk21 Sep08 | Wk22 Sep15 | Wk23 Sep22 | Wk24 Sep29
▶ SYSTEM 1 — Boiler System (2123 Kg/H)
1 | Boiler System | Design & Engineering | Technical Specs Review | Engineering | In Progress | ▶
1 | Boiler System | Design & Engineering | P&ID Drawing Approval | Engineering | Not Started |  | ▶
1 | Boiler System | Procurement | Vendor Finalization | Procurement | Complete | ▶
1 | Boiler System | Procurement | Purchase Order Issued | Procurement | Complete |  | ▶
1 | Boiler System | Procurement | Manufacturing & QC | Supplier | In Progress |  |  | ▶
1 | Boiler System | Delivery & Logistics | Shipping / Sea Freight | Logistics | Not Started | [8 empty] | ▶
1 | Boiler System | Delivery & Logistics | Customs Clearance | Logistics | Not Started | [11 empty] | ▶
1 | Boiler System | Delivery & Logistics | Site Delivery | Logistics | Not Started | [12 empty] | ▶
1 | Boiler System | Installation | Civil & Foundation Prep | Civil Contractor | Not Started | [10 empty] | ▶
1 | Boiler System | Installation | Equipment Installation | Install Team | Not Started | [13 empty] | ▶
1 | Boiler System | Installation | Piping & Connections | Install Team | Not Started | [15 empty] | ▶
1 | Boiler System | Testing & Commissioning | Factory Acceptance Test | Engineering | Not Started | [6 empty] | ▶
1 | Boiler System | Testing & Commissioning | Site Acceptance Test | Engineering | Not Started | [17 empty] | ▶
1 | Boiler System | Testing & Commissioning | Performance Verification | Engineering | Not Started | [18 empty] | ▶
▶ SYSTEM 2 — Air Compressor System (4.3 m³/H)
2 | Air Compressor System | Design & Engineering | Compressed Air Demand Audit | Engineering | In Progress | ▶
2 | Air Compressor System | Design & Engineering | Piping Layout Approval | Engineering | Not Started |  | ▶
2 | Air Compressor System | Procurement | Vendor Finalization | Procurement | Complete | ▶
2 | Air Compressor System | Procurement | Purchase Order Issued | Procurement | In Progress |  | ▶
2 | Air Compressor System | Procurement | Manufacturing & QC | Supplier | Not Started |  |  | ▶
2 | Air Compressor System | Delivery & Logistics | Shipping | Logistics | Not Started | [6 empty] | ▶
2 | Air Compressor System | Delivery & Logistics | Customs Clearance | Logistics | Not Started | [9 empty] | ▶
2 | Air Compressor System | Delivery & Logistics | Site Delivery | Logistics | Not Started | [10 empty] | ▶
2 | Air Compressor System | Installation | Compressor Room Preparation | Civil Contractor | Not Started | [8 empty] | ▶
2 | Air Compressor System | Installation | Equipment Installation | Install Team | Not Started | [11 empty] | ▶
2 | Air Compressor System | Installation | Pipe Network Connection | Install Team | Not Started | [12 empty] | ▶
2 | Air Compressor System | Testing & Commissioning | Pressure & Leak Test | Engineering | Not Started | [14 empty] | ▶
2 | Air Compressor System | Testing & Commissioning | Performance Verification | Engineering | Not Started | [15 empty] | ▶
▶ SYSTEM 3 — Water System (2760 Kg/H)
3 | Water System | Design & Engineering | Water Balance Study | Engineering | In Progress | ▶
3 | Water System | Design & Engineering | Plumbing Drawing Approval | Engineering | Not Started |  | ▶
3 | Water System | Procurement | Pump & Tank Selection | Procurement | Not Started |  | ▶
3 | Water System | Procurement | Purchase Order Issued | Procurement | Not Started |  |  |  | ▶
3 | Water System | Procurement | Manufacturing / Supply | Supplier | Not Started |  |  |  |  | ▶
3 | Water System | Delivery & Logistics | Shipping | Logistics | Not Started | [8 empty] | ▶
3 | Water System | Delivery & Logistics | Site Delivery | Logistics | Not Started | [10 empty] | ▶
3 | Water System | Installation | Trenching & Civil Works | Civil Contractor | Not Started | [9 empty] | ▶
3 | Water System | Installation | Pump & Tank Installation | Install Team | Not Started | [11 empty] | ▶
3 | Water System | Installation | Pipe Network Installation | Install Team | Not Started | [13 empty] | ▶
3 | Water System | Testing & Commissioning | Hydraulic Pressure Test | Engineering | Not Started | [15 empty] | ▶
3 | Water System | Testing & Commissioning | Flow Rate Verification | Engineering | Not Started | [16 empty] | ▶
▶ SYSTEM 4 — Weighbridge (60T)
4 | Weighbridge | Design & Engineering | Foundation Design | Engineering | Not Started |  |  | ▶
4 | Weighbridge | Procurement | Supplier Selection | Procurement | Not Started |  | ▶
4 | Weighbridge | Procurement | Purchase Order Issued | Procurement | Not Started |  |  |  | ▶
4 | Weighbridge | Procurement | Manufacturing | Supplier | Not Started |  |  |  |  | ▶
4 | Weighbridge | Delivery & Logistics | Transport to Site | Logistics | Not Started | [10 empty] | ▶
4 | Weighbridge | Installation | Foundation Construction | Civil Contractor | Not Started |  |  |  |  | ▶
4 | Weighbridge | Installation | Weighbridge Installation | Install Team | Not Started | [10 empty] | ▶
4 | Weighbridge | Installation | Electrical & Data Wiring | Electrician | Not Started | [12 empty] | ▶
4 | Weighbridge | Testing & Commissioning | Calibration & Certification | Third Party | Not Started | [13 empty] | ▶
4 | Weighbridge | Testing & Commissioning | Operational Test | Engineering | Not Started | [14 empty] | ▶
▶ SYSTEM 5 — Big Storage Oil Tank (2 × 20,000 L)
5 | Big Storage Oil Tank | Design & Engineering | Tank Specs Review (Annex D) | Engineering | In Progress | ▶
5 | Big Storage Oil Tank | Design & Engineering | Civil Foundation Design | Engineering | Not Started |  | ▶
5 | Big Storage Oil Tank | Procurement | Vendor Finalization | Procurement | Not Started |  | ▶
5 | Big Storage Oil Tank | Procurement | Purchase Order Issued | Procurement | Not Started |  |  |  | ▶
5 | Big Storage Oil Tank | Procurement | Tank Fabrication | Supplier | Not Started |  |  |  |  | ▶
5 | Big Storage Oil Tank | Delivery & Logistics | Oversized Transport Permit | Logistics | Not Started | [11 empty] | ▶
5 | Big Storage Oil Tank | Delivery & Logistics | Site Delivery | Logistics | Not Started | [12 empty] | ▶
5 | Big Storage Oil Tank | Installation | Civil Bund & Foundation | Civil Contractor | Not Started | [6 empty] | ▶
5 | Big Storage Oil Tank | Installation | Tank Erection & Anchoring | Install Team | Not Started | [12 empty] | ▶
5 | Big Storage Oil Tank | Installation | Pipework & Valves | Install Team | Not Started | [14 empty] | ▶
5 | Big Storage Oil Tank | Testing & Commissioning | Hydrostatic Test | Engineering | Not Started | [16 empty] | ▶
5 | Big Storage Oil Tank | Testing & Commissioning | Regulatory Inspection | Third Party | Not Started | [17 empty] | ▶
▶ SYSTEM 6 — Elevator (2×2T)
6 | Elevator | Design & Engineering | Structural Drawing Review | Engineering | In Progress | ▶
6 | Elevator | Design & Engineering | Drawing Mod Feedback to PFF | Engineering | Not Started |  |  | ▶
6 | Elevator | Procurement | Vendor/Supplier Finalization | Procurement | Not Started |  | ▶
6 | Elevator | Procurement | Purchase Order Issued | Procurement | Not Started |  |  |  | ▶
6 | Elevator | Procurement | Manufacturing | Supplier | Not Started |  |  |  |  | ▶
6 | Elevator | Delivery & Logistics | Shipping | Logistics | Not Started | [12 empty] | ▶
6 | Elevator | Delivery & Logistics | Customs Clearance | Logistics | Not Started | [15 empty] | ▶
6 | Elevator | Delivery & Logistics | Site Delivery | Logistics | Not Started | [16 empty] | ▶
6 | Elevator | Installation | Shaft / Structural Prep | Civil Contractor | Not Started | [8 empty] | ▶
6 | Elevator | Installation | Elevator Installation | Specialist | Not Started | [16 empty] | ▶
6 | Elevator | Installation | Electrical Connections | Electrician | Not Started | [18 empty] | ▶
6 | Elevator | Testing & Commissioning | Load Test (People & Goods) | Engineering | Not Started | [19 empty] | ▶
6 | Elevator | Testing & Commissioning | Safety Inspection & Cert. | Third Party | Not Started | [20 empty] | ▶
6 | Elevator | Testing & Commissioning | Handover & Training | Engineering | Not Started | [21 empty] | ▶
LEGEND: |  | Complete |  | In Progress |  | Not Started |  | Blocked

## Dashboard
📊 PET FACTORY MAROC — Project Dashboard
System Summary
# | System | Spec | Total Tasks | Not Started | In Progress | Complete | % Complete
1 | Boiler System | 2123 Kg/H | 14 | 10 | 2 | 2 | 14%
2 | Air Compressor System | 4.3 m³/H | 13 | 10 | 2 | 1 | 8%
3 | Water System | 2760 Kg/H | 12 | 11 | 1 | 0 | 0%
4 | Weighbridge | 60T | 10 | 10 | 0 | 0 | 0%
5 | Big Storage Oil Tank | 2 × 20,000 L | 12 | 11 | 1 | 0 | 0%
6 | Elevator | 2×2T | 14 | 13 | 1 | 0 | 0%
Key Project Milestones
Apr 21, 2026 | Project Kick-off / Tracker Start | [5 empty] | In Progress
May 31, 2026 | FAMSUN Drawing Review Deadline (Boiler + Elevator) | [5 empty] | Not Started
Jun 14, 2026 | Boiler & Compressor Factory Acceptance Tests | [5 empty] | Not Started
Jul 26, 2026 | Boiler System Site Delivery | [5 empty] | Not Started
Aug 9, 2026 | Weighbridge Foundation Complete | [5 empty] | Not Started
Sep 6, 2026 | Oil Tank Erection Complete | [5 empty] | Not Started
Sep 20, 2026 | Water & Compressor Systems Commissioned | [5 empty] | Not Started
Oct 4, 2026 | Boiler & Weighbridge Commissioned | [5 empty] | Not Started
Nov 1, 2026 | Elevator Installation Complete | [5 empty] | Not Started
Nov 29, 2026 | All Systems Commissioned — Facility Ready | [5 empty] | Not Started