## Dashboard
PetFactory Maroc — CapEx Budget Dashboard
Generated: 2026-09-10
BUDGET OVERVIEW
Total Budget | 25000000 | MAD
Contingency (10%) | 2500000 | MAD
Usable Budget | 22500000 | MAD
Total Paid | 0 | MAD
Total Committed | 0 | MAD
Total Forecasted | 19074514.22 | MAD
Total Planned Spending | 19074514.22 | MAD
Remaining Budget | 22500000 | MAD
Subsidies Expected (12m) | 7000000 | MAD
Remaining incl. Subsidies | 29500000 | MAD
Budget Utilization | 0%
PER-SYSTEM BREAKDOWN
System | Forecasted | Committed | Paid | Total | Quotes
Air Compressor System | 529214.22 | 0 | 0 | 529214.22 | 2
Aménagement Extérieur | 1500000 | 0 | 0 | 1500000 | 0
Big Storage Oil Tank | 250000 | 0 | 0 | 250000 | 0
Boiler System | 6045300 | 0 | 0 | 6045300 | 5
Electrical Installation & Transformer | 2500000 | 0 | 0 | 2500000 | 0
Elevator | 600000 | 0 | 0 | 600000 | 0
Installation GAZ | 400000 | 0 | 0 | 400000 | 0
Logiciel | 500000 | 0 | 0 | 500000 | 0
Recrutement | 300000 | 0 | 0 | 300000 | 0
Solaire Électricité | 3000000 | 0 | 0 | 3000000 | 0
Séparation Salle de Commande & MCC | 500000 | 0 | 0 | 500000 | 0
Séparation et Froid Industriel | 1800000 | 0 | 0 | 1800000 | 0
Water System | 800000 | 0 | 0 | 800000 | 0
Weighbridge | 350000 | 0 | 0 | 350000 | 0
TOTAL | 19074514.22 | 0 | 0 | 19074514.22 | 7

## Vendor Quotes
Vendor Quotes Comparison
Vendor | System | Description | Amount (MAD) | Currency | Original Amt | FX Rate | Quote Date | Valid Until | Status | Notes
Casa Comp / MARK (Atlas Copco Group) | Air Compressor System | Complete aluminum piping network DN50/DN25: tubes (15,266.50), connectors (16,687), elbows (12,328), tees (2,092), ball valves (26,748), quick drops (7,909), supports (13,680), labor (1,425), platform rental (950) | 103482.67 | MAD | 103482.67 | 1 | 2026-04-07 |  | Expired | Devis DV2600078. Piping for compressed air distribution. 5% discount applied. Linked to equipment quote 00722.
Casa Comp / MARK (Atlas Copco Group) | Air Compressor System | 2x MARK RMM37 screw compressors 37kW direct-drive (315,840), 2x MDX6500 dryers (71,928.45), 1x 2000L air receiver (25,000), filters FG79/FC79 (12,963.10). Commissioning included. | 425731.55 | MAD | 425731.55 | 1 | 2026-04-07 | 2026-05-07 | Expired | Offre 00722. 25% discount on compressors/dryers, 20% on accessories. Transport not included. Payment: 30% at order, 70% at delivery. 6-8 weeks delivery.
Fangkuai Boiler Co., LTD (China) | Boiler System | WNS3-1.0-YQ-FL1 3 t/h split condensing gas steam boiler with all auxiliaries (condenser, Riello RL310 burner, Siemens PLC control, water softener, feed pumps, steam distributor, chimney) | 424670 | USD | 42467 | 10 | 2026-06-16 | 2026-09-16 | Received | 3 t/h only - undersized for 6000 kg/h requirement. FOB China, shipping not included.
Pression Equipement / Stein Energie (ALSTOM) | Boiler System | 1x Renovated STEIN FASEL (ALSTOM) DFS 6000, 6000 Kg/h steam boiler at 16 bar, Weishaupt fioul burner, pump, controls, new armoire/wiring, new INOX insulation. Ready on chassis. | 510000 | MAD | 510000 | 1 | 2025-05-20 | 2025-06-20 | Expired | Renovated (2001 build, 2025 renovation). Fioul burner - would need gas conversion. 1 month delivery. Single boiler only, not complete boiler room.
Energie Management (Casablanca) | Boiler System | Complete boiler room: Chaudière Vapeur à Gaz 5000 Kg (400,000) + 6000 Kg (440,000), chimneys, bâche alimentaire, purges, blow-down tank, steam collector DN400, gas detendeurs, water softener, transport to Dakhla, installation/commissioning, full steam/condensate piping with insulation | 2528318.94 | MAD | 2528318.94 | 1 | 2026-03-11 |  | Under Review | Proforma 0016/2026. ICE: 002861675000028. Total before discount: 2,689,701 MAD. 6% discount applied. TTC (20% TVA): 3,033,982.72 MAD.
EGFI - Entreprise Générale de Fumisterie Industrielle | Boiler System | Complete turnkey boiler room: 2x 6000 kg/h at 12 bars (propane), wet-back design, economizers, O2 analyzers, chimneys (20m), bâche alimentaire 10,000L, osmose inverse 6 m3/h, water treatment, steam collector, blowdown tank, spare parts (1 year), montage/commissioning | 6045300 | MAD | 6045300 | 1 | 2026-07-20 |  | Under Review | Devis 315/26. Most comprehensive offer - includes water treatment, economizers, PLC/SCADA. Delivery 4.5-5 months. Dégazeur thermique price TBD. Site: QI Sidi Bouatmane.
Bosch Industrial / Robert Bosch Morocco (SAF) | Boiler System | 2x UNIVERSAL UL-S 5000 kg/h steam boilers (2,687,990.37 each), bâche alimentaire WSM-V (619,176.55), barillet distribution (172,461.38), documentation (5,526.37), commissioning/training (316,482.10) | 6489627.14 | MAD | 6489627.14 | 1 | 2024-02-12 |  | Received | Offer T100464540-35. Older quote from 2024, may need price update.

## Budget Line Items
Budget Line Items — Spending Forecast
System | Description | Amount (MAD) | Status | Expected Date | Paid Date | Vendor | PO Number | Notes
Aménagement Extérieur | External works - concrete, landscaping, drainage | 1500000 | Forecasted | 2026-11-01 |  |  |  | No quotes received yet. Estimate for béton and aménagement.
Weighbridge | Weighbridge 60T - supply and installation | 350000 | Forecasted | 2026-12-01 |  |  |  | No quotes received yet. Estimate.
Electrical Installation & Transformer | 1600 KVA transformer and electrical installation | 2500000 | Forecasted | 2026-12-15 |  |  |  | No quotes received yet. Critical path item. Estimate.
Big Storage Oil Tank | 2x 20,000L oil storage tanks | 250000 | Forecasted | 2027-01-01 |  |  |  | No quotes received yet. Estimate.
Boiler System | Boiler room equipment and installation (2x 6000 kg/h) | 6045300 | Forecasted | 2027-01-15 |  | EGFI (pending final selection) |  | Based on EGFI quote - most comprehensive. Final vendor TBD.
Installation GAZ | Gas installation - 15 m³ capacity | 400000 | Forecasted | 2027-01-15 |  |  |  | No quotes received yet. Linked to boiler system fuel supply. Estimate.
Air Compressor System | 2x 37kW screw compressors with dryers, receiver and piping | 529214.22 | Forecasted | 2027-02-01 |  | Casa Comp (quote expired, needs renewal) |  | Combined equipment (425,731.55) + piping (103,482.67). Quote expired 2026-05-07.
Séparation Salle de Commande & MCC | Control room and motor control center separation | 500000 | Forecasted | 2027-02-01 |  |  |  | No quotes received yet. Estimate.
Water System | Water system 10,000 Kg/H - equipment and installation | 800000 | Forecasted | 2027-02-15 |  |  |  | No quotes received yet. Estimate based on industry benchmarks.
Elevator | 2x 2T elevators - supply and installation | 600000 | Forecasted | 2027-03-01 |  |  |  | No quotes received yet. Estimate.
Recrutement | Recruitment of plant operations and technical staff | 300000 | Forecasted | 2027-03-01 |  |  |  | Estimate for recruitment costs including agency fees.
Séparation et Froid Industriel | Industrial refrigeration and separation systems | 1800000 | Forecasted | 2027-03-15 |  |  |  | No quotes received yet. Estimate.
Solaire Électricité | Solar electricity installation (30% of 1600 KVA = 480 KVA) | 3000000 | Forecasted | 2027-04-01 |  |  |  | No quotes received yet. Estimate for 480 KVA solar installation.
Logiciel | Software - ERP, SCADA, process control systems | 500000 | Forecasted | 2027-04-01 |  |  |  | Estimate for software licensing and implementation.
TOTAL |  | 19074514.22

## Subsidies
Subsidies & Government Support
Name | Provider | Amount (MAD) | Status | Application Date | Expected Receipt | Received Date | Conditions | Notes
Fonds de Développement Industriel (FDI) | Ministère de l'Industrie et du Commerce | 5000000 | Applied | 2026-06-01 | 2027-03-01 |  | Minimum 50 MMAD investment, job creation requirements, environmental compliance | Industrial acceleration program for agri-food sector.
Programme Tatwir - Investissement Productif | Maroc PME | 2000000 | Applied | 2026-07-15 | 2027-06-01 |  | Up to 20% of eligible investment, max 10 MMAD. Must be PME with turnover < 200 MMAD. | Covers equipment acquisition and industrial setup.
TOTAL EXPECTED |  | 7000000

## Cashflow Forecast
Monthly Cashflow Forecast (12 months)
Month | Outflows (MAD) | Subsidy Inflows (MAD) | Net (MAD) | Cumulative Net (MAD)
2026-09 | 0 | 0 | 0 | 0
2026-10 | 0 | 0 | 0 | 0
2026-11 | 1500000 | 0 | -1500000 | -1500000
2026-12 | 2850000 | 0 | -2850000 | -4350000
2027-01 | 6695300 | 0 | -6695300 | -11045300
2027-02 | 1829214.22 | 0 | -1829214.22 | -12874514.22
2027-03 | 2700000 | 5000000 | 2300000 | -10574514.22
2027-04 | 3500000 | 0 | -3500000 | -14074514.22
2027-05 | 0 | 0 | 0 | -14074514.22
2027-06 | 0 | 2000000 | 2000000 | -12074514.22
2027-07 | 0 | 0 | 0 | -12074514.22
2027-08 | 0 | 0 | 0 | -12074514.22